## Sheet1
Project Risk Analysis |  |  | Team Members: Aamera Shaikh, Mahamadoun Toure, Namratha Shivani, Chalasani, Durga Pravallika, Hemanth Kumar Reddy
Risk Number | Status | Risk Name | Description | Likelihood of Occurrence (1-5) | Impact (1-5) | Ease of Detectability (1-5) | Risk Priority Number | Date Opened | Risk Owner | Date Closed | Mitigation Strategy
1 | Closed | Delays in Requirement Gathering Phase | Potential delays in gathering stakeholder requirements or defining system functionalities could extend project timeline. | 4 | 3 | 3 | 36 | 2024-01-25 | Mahamadoun Toure | 2024-02-05 | Establish clear communication channels, set realistic expectations, implement agile methodologies, and conduct frequent stakeholder meetings.
2 | Closed | Integration Challenges | Difficulty in integrating AI-powered health monitoring software with existing healthcare systems and wearable devices may lead to compatibility issues. | 3 | 4 | 2 | 24 | 2024-02-14 | Aamera Shaikh | 2024-03-25 | Conduct thorough compatibility testing and pilot trials, collaborate closely with IT teams and vendors, allocate additional resources and time buffers.
3 | Closed | Low User Adoption | Elderly participants may exhibit reluctance or difficulty in adopting the new monitoring system due to unfamiliarity with technology or privacy concerns. | 3 | 4 | 3 | 36 | 2024-03-01 | Namratha Shivani Chalasani | 2024-03-22 | Conduct comprehensive user training, provide user-friendly documentation, engage in continuous feedback loops, and implement incentives for user engagement.
4 | Closed | System Performance Issues | The AI algorithms may encounter accuracy or efficiency issues during testing and evaluation, impacting the reliability of health data analysis. | 2 | 4 | 4 | 32 | 2024-03-01 | Aamera Shaikh | 2024-03-18 | Implement rigorous testing protocols, utilize real-world test environments, monitor performance metrics, and optimize algorithms continuously.
5 | Closed | Budget Overruns | Unforeseen expenses related to software procurement, integration, or pilot program administration could exceed the allocated project budget. | 3 | 3 | 3 | 27 | 2024-01-18 | Hemanth Kumar Reddy | 2024-02-09 | Conduct cost-benefit analyses, implement financial controls, monitor budget regularly, and maintain open communication with stakeholders.
6 | Closed | Data Privacy Breach | Inadequate measures to protect sensitive health data could result in unauthorized access or data breaches, compromising patient privacy and trust. | 2 | 5 | 2 | 20 | 2024-01-18 | Durga Pravallika | 2024-02-14 | Implement robust data security protocols, ensure compliance with privacy regulations, educate team members and users, and enforce strict access controls.
7 | Closed | Hardware Reliability Issues | Malfunctions or failures in hardware components such as sensors, wearables, or monitoring devices could compromise the accuracy and effectiveness of health monitoring | 2 | 4 | 3 | 24 | 2024-01-25 | Mahamadoun Toure | 2024-02-02 | Employ high-quality, reliable hardware components, conduct regular maintenance checks, establish protocols for quick replacement or repair, and provide user education on proper device usage and care.
8 | Closed | Staff Training and Retention | Ensuring that personnel have adequate skills and knowledge to operate and maintain the monitoring system is crucial. Staff turnover or insufficient training could lead to gaps in system utilization and support. | 3 | 3 | 3 | 27 | 2024-01-25 | Namratha Shivani Chalasani | 2024-03-04 | Develop comprehensive training programs, cross-train staff members, incentivize ongoing education and certification, and implement retention strategies such as career development opportunities and recognition programs.
9 | Closed | Dependency on Third-Party Providers | Reliance on third-party providers for key components such as cloud services, or data storage might introduce risks related to service disruptions, vendor lock-in, or changes in terms and conditions. | 3 | 4 | 3 | 36 | 2024-02-08 | Hemanth Kumar Reddy | 2024-03-26 | Diversify vendors, negotiate strong SLAs, prepare for interruptions, review performance regularly, monitor industry trends and regulations.
10 | Closed | False Positive or Negative Alerts | The monitoring system may generate false positive or negative alerts, leading to unnecessary interventions or overlooking critical health issues. | 3 | 3 | 2 | 18 | 2024-03-01 | Durga Pravallika | 2024-03-28 | Deploy algorithms to reduce false alerts, create protocols for verifying alerts, educate users on accurate interpretation, and regularly assess alert accuracy and effectiveness.
1. Prioritize your risks according to their RPN
2. Provide a risk mitigation strategy for each risk